## Slide 1
Content
Launch
Design
Electronic Newsletter
Finished Website
Hosting
Home page
Company history
Board of directors
Values
About us
Client communication
Product 1
Product 2
Product 3
Products
Colour-scheme
Header
Footer
Design template
Logo
Photos
Illustrations
Design elements
Blog
Web-address
Service Agreement
Videos
Contact us
Finance department
Sales department
Internal training
Product Breakdown Structure
Susanne Madsen International Ltd – www.susannemadsen.com
Notes: The Product Breakdown Structure (PBS) is a logical breakdown of all the components or sub-products that your project’s finished product consists of. These are not activities, but products which can be described, quality tested and delivered.
The above example relates to a website project, where the final website is the end product. To create your own PBS, delete the text in the boxes and customize to your project.
For more information, check out www.susannemadsen.com and “The Project Management Coaching Workbook” on Amazon.

## Slide 2
Electronic Newsletter
Finished Website
Client communication
Colour-scheme
Header
Footer
Design template
Logo
Photos
Illustrations
Design elements
Web-address
Service Agreement
Videos
Finance department
Sales department
Internal training
Product Flow Diagram
Home page
Company history
Board of directors
Values
About us
Product 1
Product 2
Product 3
Products
Blog
Contact us
Susanne Madsen International Ltd – www.susannemadsen.com
Notes: The Product Flow Diagram is a logical sequencing of the elements or sub-products of your PBS. It takes into consideration dependencies between the sub-products you have identified and provides the flow between them, i.e. which products need to be produced first, second and last.

## Slide 3
Further Information
www.susannemadsen.com
www.powerofprojectleadership

## Slide 4
International project leadership coach
20 years hands-on experience leading change programmes of up to $30m
Fully qualified coach and NLP Practitioner
PRINCE2 and MSP Practitioner
Author of The Power of Project Leadership (now in 2nd edition) and The Project Management Coaching Workbook.
Visit Susanne’s website http://www.susannemadsen.com
Susanne Madsen