## High Level Budget Tracking
Project Name | Project xx
Sponsor | Name
Project Manager | Name
Fiancial Year | 2013
RAG Status | RED
Workstream / Product | Approved Budget / Cost Estimate ($) | Actual Spend to Date | Percentage Budget used | Budget Remaining | Cost of Work Remaining | Estimate at Completion | Variance
PRODUCT 1 | 1022000 | 798008 | 78.08% | 223992 | 450000 | 1248008 | -226008
PRODUCT 2 | 900000 | 233009 | 25.89% | 666991 | 560000 | 793009 | 106991
PRODUCT 3 | 1010000 | 978445 | 96.88% | 31555 | 5500 | 983945 | 26055
PRODUCT 4 | 550000 | 703557 | 127.9% | -153557 | 0 | 703557 | -153557
PRODUCT 5 | 228000 | 23000 | 10.09% | 205000 | 0 | 23000 | 205000
PRODUCT 6 | 887000 | 410149 | 46.24% | 476851 | 480000 | 890149 | -3149
TOTAL BUDGET | 4597000 | 3146168 | 68.44% | 1450832 | 1495500 | 4641668 | -44668
All numbers are USD
This table should be your high level budget tracking sheet which you can use as your overall dashboard. It provides an overview of your project's financial situation at a particular point in time - hence it's a snapshot. This is the overview you should be reporting from in your weekly status reports and to the steering committee. This sheet will take information from other more detailed sheets depending on how you want to track your actual costs and how you produce your estimates. The next two sheets contain 1) an example of a Detailed Resources Cost Tracking sheet and 2) an example of a Burn-Up Chart. Note that the have no particular correlation to this high level sheet.
Note on B10: List the workstreams or products whose cost you want to track.
Note on C10: Insert the budget or baseline estiamte which you want to track to. This number is your starting point and stays constant throughout your project.
Note on D10: As the project progresses, record the actual spend per month per product or workstream. This field shows the aggregated total spend to date per product/workstream. The actual cost is based on invoices and timesheet submissions and is provided by your finance department.
Note on E10: Calculate the percentage of approved budget spent to date. That's Column D divided by Colum C.
Note on G10: Cost of remaining work is your estiamte for how much money will you need to complete the delivery of that workstream or product.
Note on H10: Estimate at completion is your total estimate for completing that workstream, i.e. it's the "Actual spend to Date" (column D) plus the "Cost of Work Remaining" (column G).
Note on I10: The variance shows the difference between your budget (or initial cost estimate of column C) and your "Estimate of Completion" (column H).
Note on F10: Budget remaining is simply"Approved Budget" (column C) minus "Actual Spend" (column D).

## Detailed Resource Cost Tracking
Detailed Resource Cost Tracking - over time
If your project costs are driven by human resource utilisation, you can use the below sheet to track the cost of your resources to ensure your resource plan stacks up against your estimates and budgets. The first part of this table (Q2) illustrates actual costs (as we imagine Q2 has passed). The second part (Q3 and Q4) illustrates estimated resource costs as we imagine Q3 and Q4 are still to take place. This example project runs from April to November only. As each month passes you update the estimated costs with actual cost (provided by finance). The advantage of this sheet is that it provides you with a total overview of all estimated and actual (human) resource costs which you can then compare to your budget.
[7 empty] | Q2 - (Actual Spend) |  |  | Q3 - (Estimated Spend) |  |  |  | Q4 - Estimated
Expense Type | Resource Name | PRCC | Status | Business | Utilisation Rate (%) | Daily Rate | Apr | May | Jun | Jul | Aug | Sep |  | Oct | Nov | Total Actual Spend | Cost of Remaining Work | Estimate at Completion
[7 empty] | 334526.58 | 406138.89 | 473339.1 | 534654.2 | 544085.8 | 483357.8 |  | 339709.6 | 213908 | 1214004.57 | 2115715.4 | 3329719.97
Project Management | Person Name 1 | 23614 | P | Technology | 100% | 1575 | 24600.03 | 24600.03 | 24600.03 | 28350 | 28350 | 28350 |  | 28350 | 28350
Project Support | Person Name 2 | 23616 | P | Technology | 70% | 1231 | 0 | 13000 | 13000 | 15510.6 | 15510.6 | 15510.6 |  | 0 | 0
Technical Management | Person Name 3 | 23626 | P | Business | 100% | 1575 | 24600.03 | 18000 | 24600.03 | 28350 | 28350 | 28350 |  | 28350 | 28350
Technical Management | Person Name 4 | 23614 | P | Technology | 80% | 1575 | 0 | 16000.8 | 16000.8 | 22680 | 22680 | 22680 |  | 0 | 0
QA / test Management | Person Name 5 | 23623 | P | Business | 100% | 1575 | 24600.03 | 24600.03 | 24600.03 | 28350 | 28350 | 28350 |  | 28350 | 28350
Tester | Person Name 6 | 23623 | T | Business | 100% | 1231 | 21900 | 21900 | 21900 | 22158 | 22158 | 22158 |  | 22158 | 22158
Tester | Person Name 7 | 23623 | P | Business | 20% | 1060 | 0 | 2900.81 | 2900.81 | 3816 | 3816 | 3816 |  | 3816 | 0
Tester | Person Name 8 | 23623 | T | Business | 100% | 1060 | 0 | 0 | 15009.3 | 19080 | 19080 | 19080 |  | 19080 | 0
Busines Analysis | Person Name 9 | 23623 | P | Business | 80% | 1575 | 16000.8 | 10000 | 16000.8 | 22680 | 22680 | 22680 |  | 0 | 0
Busines Analysis | Person Name 10 |  |  |  | 70% | 1575 | 16000.8 | 16000.8 | 16000.8 | 19845 | 19845 | 0 |  | 0 | 0
Architect | Person Name 11 | 23623 | P | Business | 80% | 1575 | 16000.8 | 16000.8 | 16000.8 | 22680 | 22680 | 22680 |  | 0 | 0
Architect | Person Name 12 | 23623 | P | Business | 100% | 1575 | 24600.03 | 10000 | 24600.03 | 28350 | 28350 | 28350 |  | 0 | 0
Infrastructure | Person Name 13 | 23623 | P | Business | 50% | 1231 | 0 | 0 | 11079 | 11079 | 11079 | 11079 |  | 0 | 0
Infrastructure | Person Name 14 | 23623 | P | Business | 50% | 1231 | 0 | 0 | 11079 | 11079 | 11079 | 0 |  | 0 | 0
Product Development | Person Name 15 | 23614 | P | Technology | 100% | 1575 | 24600.03 | 24600.03 | 24600.03 | 28350 | 28350 | 28350 |  | 28350 | 28350
Product Development | Person Name 16 | 23623 | P | Business | 100% | 1575 | 24600.03 | 24600.03 | 24600.03 | 28350 | 28350 | 28350 |  | 28350 | 28350
Product Development | Person Name 17 | 0 | Left in Feb | Technology | 100% | 1231 | 21900 | 21900 | 21900 | 22158 | 22158 | 22158 |  | 22158 | 0
Product Development | Person Name 18 | 23614 | T | Technology | 50% | 1231 | 11079 | 11079 | 9333.55 | 11079 | 11079 | 11079 |  | 11079 | 0
Product Development | Person Name 19 | 23623 | P | Business | 50% | 1231 | 11079 | 11079 | 11079 | 11079 | 11079 | 11079 |  | 11079 | 0
Product Development | Person Name 20 | 23614 | T | Technology | 20% | 1231 | 0 | 3500.78 | 3500.78 | 4431.6 | 4431.6 | 4431.6 |  | 0 | 0
Product Development | Person Name 21 | 23623 | P | Business | 20% | 1060 | 0 | 3500.78 | 3500.78 | 3816 | 3816 |  |  | 0 | 0
Product Development | Person Name 22 | 23614 | P | Technology | 50% | 1060 | 0 | 0 | 5900.5 | 9540 | 9540 |  |  | 0 | 0
Risk Management | Person Name 23 | 23614 | P | Technology | 60% | 1060 | 11079 | 11079 | 11079 | 11448 | 11448 |  |  | 0 | 0
Implementation | Person Name 24 |  |  |  | 100% | 1231 | 0 | 0 | 21900 | 22158 | 22158 | 22158 |  | 22158 | 0
Training | Person Name 25 | 23616 | P | Technology | 20% | 1231 | 0 | 0 | 0 | 0 | 4431.6 | 4431.6 |  | 4431.6 | 0
Data analysis | Person Name 26 | 23616 | T | Technology | 100% | 1231 | 0 | 21900 | 21900 | 22158 | 22158 | 22158 |  | 0 | 0
Data analysis | Person Name 27 | 23616 | T | Technology | 50% | 1231 | 0 | 8889 | 8889 | 11079 | 11079 | 11079 |  | 0 | 0
Fixed cost | Description | [5 empty] | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
Variable cost | Description | [5 empty] | 11887 | 41008 | 17785 | 15000 | 20000 | 15000 |  | 32000 | 0
Note on I7: In this example we assume that Q2 has passed and all figures are actual numbers (costs) provided by finance.
Note on M7: In this example we assume that Q3 has not yet taken place, hence all number are estimated, in this case based on expected resource utilisation (column F x column G x 20 days)
Note on S8: This is columns I+J+K as we assume Q2 has already passed.
Note on T8: Cost of Remaining Work is columns M-R as these are the resources we will need in order to still complete the project.
Note on U8: This is the total Estimate for the project, taken into consideration actual cost to date, hence colunm S+T.

## Burn-up chart
Burn-up Chart
Burn-up charts are ideal for illustrating to your stakeholders in a visual way how much money you have burnt compared to budget. You can also create a burn-down chart which works in exaclty the same way. In this example, the total budget is $340,000 as illustrated by the constant (horizontal) blue line.The yellow line shows your planned incremental spend, i.e. how you plan to spend your budget over the duration of the project. This will be derived from your project estimates and resources shededule. Finally, use the pink line to show - month by month - how much money you actually are spending compared to plan. Burn-up charts are very simple yet powerful tools.You can read more about them in the Project Management Coaching Workbook (see next sheet).
Approved Budget / Cost Estimate | Actual Incremental Spend | Planned Incremental Spend | Time (weeks)
340000 | 10000 | 10000 | 1
340000 | 25000 | 20000 | 2
340000 | 40000 | 30000 | 3
340000 | 60000 | 45000 | 4
340000 | 90000 | 60000 | 5
340000 | 130000 | 90000 | 6
340000 | 180000 | 130000 | 7
340000 | 245000 | 180000 | 8
340000 |  | 230000 | 9
340000 |  | 265000 | 10
340000 |  | 290000 | 11
340000 |  | 305000 | 12
340000 |  | 315000 | 13
340000 |  | 320000 | 14
340000 |  | 325000 | 15
340000 |  | 330000 | 16
340000 |  | 340000 | 17
18
19
20
21

## Further Information
For projects to succeed and add lasting value, the project manager must be able to strategize, innovate, take risks, empower and collaborate – in other words, project managers must learn how to lead. The Power of Project Leadership - now in it's second edition - helps you transform from project manager to effective project leader by shifting your managerial and task-oriented mind-set into one of inspiration, motivation and collaboration. It explains what good project leadership looks like and shows you how to make the transition by using concrete tools and strategies. It has a practical and engaging approach and references over 25 interviews with project management thought leaders from around the world, who themselves have made the transition from project manager to project leader. The Power of Project Leadership helps you transform from project manager to effective project leader by shifting your managerial and task-oriented mind-set into one of inspiration, motivation and collaboration. It explains what good project leadership looks like and shows you how to make the transition by using concrete tools and strategies. It has a practical and engaging approach and references over 25 interviews with project management thought leaders from around the world, who themselves have made the transition from project manager to project leader.
www.powerofprojectleadership.com
Starting with an insightful self-assessment, The Project Management Coaching Workbook: Six Steps to Unleashing Your Potential offers tools, questions, reviews, guiding practices, and exercises that will help you build your roadmap to project management and leadership success. Based on her many years as a sought-after project manager, coach and mentor, Susanne Madsen offers a proven six-step method designed to help you understand and articulate what you want to achieve—and then assists you in achieving those goals. Whether used as a personal guide or in a workshop or group setting, The Project Management Coaching Workbook lays out a sound, proven plan to help you build confidence and achieve your project management goals.
www.susannemadsen.com